## TEND53
Invoice مستخلص A New Intake and raw water line for Old Damietta Water Treatment Plant
Governorate الشركة التابعة : Damietta |  |  |  | Contract Ref. no. عقد رقم : |  | DM-WS-P1AG-016/1
Invoice No: (16) : رقم المستخلص : | [7 empty] | Handing Over Site Date: | 2012-08-28 | تاريخ استلام الموقع :
Contractor : El-Nasr Co.For Facilies & Installation |  |  |  | Implementation Period 44 month فترة التنفيذ |  |  |  | Actual Starting Date : | 2012-08-28 | :تاريخ البدء الفعلى
| Original Contract Value قيمة العقد الأصلية : | 47657847.29 | [5 empty] | Official Ending Date : | 30/4/2016 | تاريخ النهو الرسمي :
| Variation Orders Value قيمة الأعمال الأضافية : | 160766.72 | [5 empty] | Actual Ending Date : |  | : تاريخ النهو الفعلي
|  | Final Contract Value قيمة العقد النهائية : |  |  | 47818614.01 |  |  |  | 30/6 /2019 | الاعمال حتى تاريخ: |  |  |  |  | 91.8
Item No. | Description | Unit الوحدة | Prices & Quantities List جدول الفئات |  | Quantities الكميات |  |  | Total prices اجمالى الاعمال | Technical Deductions استقطاعات فنية |  | Implementation التنفيذ % | Comments / Remarks ملاحظــــــــــــــــــــات | Total Prices after deductions اجمالى صافى الاعمال
|  |  | Quantities الكمية | Unit Price سعر الوحدة | Previous سابق | Current حالى | Total اجمالى |  | Penalties خصومات | Retention تعليات
Civil Works
1 | Raw water pump station works :
1.1 | Excavation and replacment work
1.1.1 | Excavation for the foundation of the building. The unit price includes; a) Excavation up to 2.40 m depth b) Shallow dewatering system by a safe and scientific method that does not effect on neighbors construction stability. c) Transport the results of excavation to the main places that prepared for that. d) Supplying all required machines to finish the work according to the approved drawings and technical specifications. The unit price also includes the filling around foundation by good supplied sands to the average level of ground surface. | m3 | 762 | 32 | 539.73 | 0 | 539.73 | 17271.36 |  | 0% | 70.83% |  | 17271.36
1.1.2 | Supplying and construction of a replacement soil under the foundation, from good supplied sands, in layers, the thickness of each layer should not be less than 25 cm, including compaction and all required tests according to soil research and foundation report. The unit price includes all required works to finish the work according to the approved drawings and technical specifications | m3 | 318 | 55 | 117.33 | 0 | 117.33 | 6453.15 |  | 0% | 36.9% |  | 6453.15
1.2 | Plain and Reinforced concrete works:
1.2.1 | Supplying and pouring of plain concrete for the foundation consists of 0.8 m3 gravel, 0.4 m3 sand and 250 kg/m3 Portland sulphate resistant cement to get strength (&2g) not less than 200 kg/cm2 according to the approved drawings and technical specifications. | m3 | 113 | 446 | 67.38 | 0 | 67.38 | 30051.48 |  | 0% | 59.63% |  | 30051.48
1.2.2 | Supplying and construction of plain concrete for floors, with thickness of 10 cm, consists of 0.8 m3 gravel, 0.4 m3 sand and 250 kg/m3 of Portland cement, strength (fc28) not less than 200 kg/cm2 according to the approved drawings and technical specifications. | m2 | 184 | 45 | 186.23 | 0 | 186.23 | 8380.35 |  | 0% | 101.2% | تم زيادة الكمية طبقا لأمر الشغل رقم 2 | 8380.35
1.2.3 | Supplying and construction of plain concrete for floors, with thickness of 15 cm, consists of 0.8 m3 gravel, 0.4 m3 sand and 250 kg/m3 of Portland cement, strength (fc2g) not less than 200 kg/cm2 according to the approved drawings and technical specifications. | m2 | 184 | 67 | 186.23 | 0 | 186.23 | 12477.41 |  | 0% | 101.2% | تم زيادة الكمية طبقا لأمر الشغل رقم 2 | 12477.41
1.2.4 | Supplying and construction of plain concrete(7 cm average thickness) for deck roofs, including the slopes and all required works to finish the workaccording to the approved drawings and technical specifications. | m2 | 225 | 32 | 238.5 | 0 | 238.5 | 7632 |  | 0% | 106% | تم زيادة الكمية طبقا لأمر الشغل رقم 2 | 7632
1.2.5 | Supplying and construction of plain concrete for entrance ramps with light reinforcements 6 $8 mm/mv in both direction, consists of 0.8 m3 gravel, 0.4 m3 sand and 250 kgm/m3 of Portland sulphate resistant cement according to the approved drawings and technical specifications. | m2 | 5 | 140 | 5 | 0 | 5 | 700 |  | 0% | 100% |  | 700
1.2.6 | Supplying and construction of reinforced concrete for the foundation consists of 0.8 m3 gravel, 0.4 m3 sand and 400 kg/m3 of Portland sulphate resistant cement, strength (fc2s) not less than 300 kg/cm2 according to the approved drawings and technical specifications. | m3 | 37 | 1030 | 43.62 | 0 | 43.62 | 44928.6 |  | 0% | 117.9% | تم زيادة الكمية طبقا لأمر الشغل رقم 2 | 44928.6
1.2.7 | Supplying and construction of reinforced concrete for columns, ceilings, stairs and all reinforced concrete works over the top level of the foundation, consists of 0.8 m3 gravel, 0.4 m3 sand and 350 kg/m3 of Portland cement to get strength (fc2s) not less than 300 kg/cm2according to the approved drawings and technical specifications. | m3 | 61 | 1300 | 82.65 | 0 | 82.65 | 107445 |  | 0% | 135.5% | تم زيادة الكمية طبقا لأمر الشغل رقم 2 | 107445
1.3 | Bases of pumps:
1.3.1 | Supplying and pouring of plain concrete for the bases ofpumps, consists of 0.8 m3 gravel, 0.4 m3 sand and 250 kg/m3 Portland cement, strength (fc2s) not less than 200 kg/cm2 according to the approved drawings andtechnical specifications. | m3 | 4 | 446 | 2.99 | 0 | 2.99 | 1333.54 |  | 0% | 74.75% |  | 1333.54
1.3.2 | Supplying and construction of reinforced concrete for the bases of pumps, consists of 0.8 m3 gravel, 0.4 m3 sand and 350 kg/m3 Portland sulphate resistant cement, strength (fc2s) not less than 300 kg/cm2 according to the approved drawings and technical specifications. | m3 | 8 | 1300 | 17.94 | 0 | 17.94 | 23322 |  | 0% | 224.3% | تم زيادة الكمية طبقا لأمر الشغل رقم 2 | 23322
1.4 | Insulation Works
1.4.1 | Supplying and laying of water proofing insulation for the reinforced concrete of the foundation to 15 cm above the ground surface, consists of 3 layers of hot oxided bitumen according to the approved drawings and technical specifications. | m2 | 214 | 25 | 248.13 | 0 | 248.13 | 6203.25 |  | 0% | 115.9% | تم زيادة الكمية طبقا لأمر الشغل رقم 2 | 6203.25
1.4.2 | Supplying and making of water proofing coating consists of one layer of insuplast non - woven polyester for deck roofs, floors and path rooms. The unit price includes all required works to finish the work according to the approved drawings and technical specifications | m2 | 409 | 65 | 437.69 | 0 | 437.69 | 28449.85 |  | 0% | 107% | تم زيادة الكمية طبقا لأمر الشغل رقم 2 | 28449.85
1.4.3 | Supplying and making of a heat insulation layer, for deck roofs, from polyethylene foam 5 cm thickness. The unit price includes all required works to finish the work according to the approved drawings and technical specifications. | m2 | 225 | 85 | 238.5 | 0 | 238.5 | 20272.5 |  | 0% | 106% | تم زيادة الكمية طبقا لأمر الشغل رقم 2 | 20272.5
| المقاول contractor | الاستشارى consultant |  |  | PIU Manager رئيس وحدة تنفيذ المشروع | [6 empty] | اجمالي الصفحة | 314920.49
| Signed التوقيع : | Signed التوقيع : |  |  | Signed التوقيع :
| Date التاريخ: | Date التاريخ: |  |  | Date التاريخ:
Chairman رئيس مجلس إدارة الشركة
Signed التوقيع :
Date التاريخ:
| ما قبله | [11 empty] | 314920.49
1.5 | Brick wall works
1.5.1 | Supplying and construction of sand brick walls for external walls of the building, according to the approved drawing and technical specifications. | m2 | 49 | 66 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
1.6 | finishing works
1.6.1 | general civil specification) (Drg.No.(6) Class.Arch.) Supplying and making of cement plastering for internal walls and ceilings, consists of 350 kg of Portland cement for each cubic meter of sand according to the approved drawings and technical specifications. | m2 | 460 | 23 | 386.85 | 0 | 386.85 | 8897.55 |  | 0% | 84.1% |  | 8897.55
1.6.2 | Supplying and making of external smooth render (fetisa), with a required colour, consists of three layers for facades, according to the approved drawings and technical specifications. | m2 | 119 | 30 | 220.4 | 0 | 220.4 | 6612 |  | 25% | 185.2% | تم زيادة الكمية طبقا لأمر الشغل رقم 2 | 4959
1.6.3 | Supplying and making of external cement skirting with a required colour for facades, according to the approved drawings and technical specifications. | m2 | 40 | 28 | 40.8 | 0 | 40.8 | 1142.4 |  | 25% | 102% | تم زيادة الكمية طبقا لأمر الشغل رقم 2 | 856.8
1.7 | Internal paints works
1.7.1 | (Section 2.2.3.9 of general civil specification) (Drg.No.(6) Class.Arch.) Supplying, and painting of plastic paints on the internal cement plastering for ceiling and walls according to the approved drawings and technical specifications. | m2 | 460 | 20 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
1.8 | tiles works
1.8.1 | (Section 2.2.3.15 of general civil specification) (Drg.No.(6) Class.Arch.) Supplying and bonding of cement tiles with dimensions of 20 * 20 * 2 cm for deck roofs. The unit price includes the skirting with height of 20 cm according to the approved drawings and technical specifications | m2 | 225 | 25 | 238.5 | 0 | 238.5 | 5962.5 |  | 0% | 106% | تم زيادة الكمية طبقا لأمر الشغل رقم 2 | 5962.5
1.8.2 | Supplying and bonding of friction resistant ceramic tiles for floors, thickness not less than 0.8cm, with a required colour, according to the approved drawings and technical specifications. | m2 | 184 | 80 | 135.1 | 0 | 135.1 | 10808 |  | 5% | 73.42% |  | 10267.6
1.8.3 | Supplying and bonding of ceramic tiles for walls, thickness not less than 0.8 cm, with a required colour, according to the approved drawings and technical specifications. | m2 | 130 | 60 | 149.45 | 0 | 149.45 | 8967 |  | 0% | 115% | تم زيادة الكمية طبقا لأمر الشغل رقم 2 | 8967
1.9 | Sanitary works
1.9.1 | Supplying and fixing of uP.V.C greygory 4 inches diameter, for deck roof rain drainage. The unit price includes supplying and fixing of U.P.V.C plastic pipes 4 inches diameter, Fixed vertically on outside external walls for deck roof rains drainage. It also includes joints, elbows, anchors and all required works to finish the work according to the approved drawings and technical specifications. | no | 1 | 750 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
1.10 | steel works
1.10.1 | Supplying, manufecturing and fixing of a steel door, with dimensions of (4.0m x 4.25m), consists of two sliding panels on a horizontal track in the floor. The unit price includes steel frames and accessories. It also includes welding, painting and all required works to finish the work according to the approved drawings and technical specifications. | kg | 1200 | 12 | 1005 | 0 | 1005 | 12060 |  | 10% | 83.75% | لحين نهو الأعمال | 10854
1.11 | Alumetal works
1.11.1 | Supplying and fixing of an alumetal window with dimensions of (4.60m x 1.00m), consists of 14 moving panels on a horizontal axis, including 6 mm thickness glass and accessories. The unit price includes, supplying and fixing of wooden frames from Sweden no 1 type with a section of 2\\ x 5\\ including its painting. It also includes all required works to finish the work according to the approved drawings and technical specifications. | no | 7 | 2500 | 7 | 0 | 7 | 17500 |  | 0% | 100% |  | 17500
2 | Land scape works
2.1.1 | Supplying and construction of plain concrete (bardowra) lines, with dimensions of 15x30x50 cm, supported on a plain concrete layer with a section of 15x30cm. -The used plain concrete consists of 0.8 m3 gravel, 0.4m3 sand and 300 kg/m3 of Portland cement. -The cement content in the used mortar is 350kg of Portland cement for each cubic meter of sand. -The unit price includes excavation, levels adjustment and all required works to finish the work according to the approved drawings and technical specifications | m | 1100 | 65 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
2.1.2 | Supplying and pouring of plain concrete with thickness of 15 cm for floors under the sidewalks tiles, consists of 0.8 m3 gravel, 0.4 m3 sand and 250 kg/m3 of Portland cement, strength (fc2s) not less than 200 kg/cm2 . -The unit price includes all required works to finish the work according to the approved drawings and technical specifications. | m2 | 1010 | 85 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
2.1.3 | Supplying and construction of reinforced concrete slabs with dimensions of 2mx2m and thickness of 20cm for floors, consists of 0.8 m3 gravel, 0.4 m3 sand and 350 kg/m3 of Portland cement, with reinforcements of 6 ^ 8mm/mv in both directions, (fc2s) not less than 300 kg/cm2. -The unit price includes the gravel soil with thickness of 30cm under the reinforced concrete slabs of the floors. -It also includes the compaction and all required tests according to the approved drawings and technical specifications. | m2 | 3712 | 165 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
| المقاول contractor | الاستشارى consultant |  |  |  | PIU Manager رئيس وحدة تنفيذ المشروع | [5 empty] | اجمالي الصفحة | 383184.94
| Signed التوقيع : | Signed التوقيع : |  |  | Signed التوقيع :
| Date التاريخ: | Date التاريخ: |  |  | Date التاريخ:
Chairman رئيس مجلس إدارة الشركة
Signed التوقيع :
Date التاريخ:
| ما قبله | [11 empty] | 383184.94
2.1.4 | Supplying and construction of steel Crete tiles for floors, with required dimensions and colours.-The unit price includes all required works to finish thework according to the approved drawings and technicalspecifications. | m2 | 1010 | 35 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
2.1.5 | Lump sum removing of existing old buildings ( Filters and shed): - The unit price includes ; a) Destruction of all plain and reinforced concrete under and over the ground surface level. b) Uninstalling, removing and transporting containers of the existing old plant where new buildings will be constructed as shown in the tender drawings (layout before and after upgrading). c) Transporting all the destruction results to another site and cleaning the places that prepared for new units according to the owner and supervision staff requirements . d) Removing all obstacles which facing are the work in removing old building such as as pipes, cables without claims for any additional cost or time. | L.s | 1 | 500000 | 0.1 | 0 | 0.1 | 50000 |  | 0% | 10% |  | 50000
2.1.6 | Supplying and fixing of rain drainage catch basins. -The unit price includes all required works to finish the work according to the approved drawings and technical specifications. | no | 7 | 3500 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
3 | Alum and chemicals building works | [6 empty] | 0
3.1 | Excavation and filling works: | [6 empty] | 0
3.1.1 | Excavation for the foundation of the building. The unit price includes; a) Excavation up to 2.40 m depth b) Shallow dewatering system by a safe and scientific method that does not effect on neighbors construction stability. c) Transport the results of excavation to the main places that prepared for that. d) Supplying all required machines to finish the work according to the approved drawings and technical specifications. The unit price also includes the filling around foundation by good supplied sands to the average level of ground surface. | m3 | 713 | 32 | 713 | 0 | 713 | 22816 |  | 0% | 100% |  | 22816
3.1.2 | Supplying and construction of a replacement soil under the foundation, from graduated gravel, with a thickness of 50 cm in two layers, including compaction and all required tests according to soil research and foundation report. The unit price includes all required works to finish the work according to the approved drawings and technical specifications. | m3 | 298 | 55 | 298 | 0 | 298 | 16390 |  | 0% | 100% |  | 16390
3.1.3 | Supplying and pouring of plain concrete for the foundation consists of 0.8 m3 gravel, 0.4 m3 sand and 250 kg/m3 Portland sulphate resistant cement to get strength (fc2s) not less than 200 kg/cm2 according to the approved drawings and technical specifications | m3 | 106 | 446 | 106 | 0 | 106 | 47276 |  | 0% | 100% |  | 47276
3.1.4 | Supplying and construction of reinforced concrete for the foundation of the building, consists of 0.8 m3 gravel, 0.4 m3 sand and 400 kg/m3 of Portland sulphate resistant cement, strength (fc2s) not less than 300 kg/cm2 according to approved drawings and technical specifications. | m3 | 55 | 1270 | 55 | 0 | 55 | 69850 |  | 0% | 100% |  | 69850
3.1.5 | Supplying and construction of plain concrete for entrance ramps with light reinforcements (6 <t>6 mm/mx in both direction) consists of 0.8 m3 gravel, 0.4 m3 sand and 250 kgm/m3 of Portland sulphate resistant cement according to the approved drawings and technical specifications. | m2 | 3 | 140 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
3.1.6 | Supplying and construction of reinforced concrete for columns, ceilings, stairs and all reinforced concreteworks over the top level of the foundation, consists of 0.8 m3 gravel, 0.4 m3 sand and 350 kg/m3 of Portland cement, strength (fc2s) not less than 300 kg/cm2according to the approved drawings and technical specifications. | m3 | 121 | 1300 | 109.53 | 0 | 109.53 | 142389 | 1.5% | 0% | 90.52% | لسوء المصنعية | 140253.165
3.1.7 | Supplying and construction of plain concrete for floors, with thickness of 10 cm, consists of 0.8 m3 gravel, 0.4 m3 sand and 250 kg/m3 of Portland sulphate resistant cement, strength (fc2s) not less than 200 kg/cm2 according to the approved drawings and technical | m2 | 120 | 45 | 120 | 0 | 120 | 5400 |  | 10% | 100% | لحين ورود شهادة تكسير المكعبات | 4860
3.1.8 | Supplying and construction of plain concrete for floors, with thickness of 15 cm consists of 0.8 m3 gravel, 0.4 m3 sand and 250 kg/m3 of Portland sulphate resistant cement, strength (fc2s) not less than 200 kg/cm2 according to the approved drawings and technical | m2 | 120 | 67 | 120 | 0 | 120 | 8040 |  | 10% | 100% | لحين ورود شهادة تكسير المكعبات | 7236
3.1.9 | general civil specification) rDrg.No.(16) Class.Hvdr.) Supplying and construction of plain concrete for the bases of pumps according to the approved drawings and technical specifications. | m3 | 5 | 446 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
3.2 | Insulation Works | [6 empty] | 0
3.2.1 | Supplying and laying of water proofing insulation for the reinforced concrete of the foundation to 15 cm above the ground surface, consists of 3 layers of hot oxided bitumen according to the approved drawings and technical specifications. | m2 | 212 | 25 | 212 | 0 | 212 | 5300 |  | 0% | 100% |  | 5300
3.2.2 | Supplying and making of water proofing coating consists of one layer of insuplast non - woven polyester for deck roofs, floors and path rooms. The unit price includes all required works to finish the work according to the approved drawings and technical specifications. | m2 | 300 | 65 | 300 | 0 | 300 | 19500 |  | 0% | 100% |  | 19500
| المقاول contractor | الاستشارى consultant |  |  |  | PIU Manager رئيس وحدة تنفيذ المشروع | [5 empty] | اجمالي الصفحة | 766666.105
| Signed التوقيع : | Signed التوقيع : |  |  | Signed التوقيع :
| Date التاريخ: | Date التاريخ: |  |  | Date التاريخ: |  |  |  |  | Chairman رئيس مجلس إدارة الشركة
Signed التوقيع :
Date التاريخ:
| ما قبله | [11 empty] | 766666.105
3.2.3 | Supplying and making of a heat insulation layer for deck roofs, from polyethylene foam 5 cm thickness, according to the approved drawings and technical specifications. | m2 | 212 | 85 | 212 | 0 | 212 | 18020 |  | 0% | 100% |  | 18020
3.2.4 | Supplying and construction of plain concrete (7 cm average thickness) for deck roofs including the slopes and all required works to finish the work according to the approved drawings and technical specifications. | m2 | 212 | 32 | 212 | 0 | 212 | 6784 |  | 0% | 100% |  | 6784
3.3 | Brick wall works
3.3.1 | Supplying and construction of (tafly) brick walls with dimensions of 25x12x6 cm, the cement content in the used mortal is350 kg for cubic meter of sand, according to the approved drawings and technical specifications. | m3 | 27 | 400 | 24 | 0 | 24 | 9600 |  | 0% | 88.89% |  | 9600
3.3.2 | Supplying and construction of sand brick walls with dimensions 25x12x6 cm for external walls of the building. The cement content in used mortar is 350 kg for cubic meter of sand, according to the approved drawing and technical specifications. | m3 | 40 | 500 | 40 | 0 | 40 | 20000 |  |  | 100% |  | 20000
3.3.3 | Supplying and construction of cement brick walls 25x12x6 cm. The cement content in used mortar is 350 kg of Portland sulphate resistant cement for each cubic meter of sand according to the approved drawings and technical specifications. | m3 | 22 | 400 | 20 | 0 | 20 | 8000 |  | 0% | 90.91% |  | 8000
3.4 | finishing works
3.4.1 | Supplying and making of internal cement plastering for ceilings and beams, consists of 350 kg of Portland cement for cubic meter of sand according to the approved drawings and technical specifications. | m2 | 250 | 23 | 250 | 0 | 250 | 5750 |  | 0% | 100% |  | 5750
3.4.2 | Supplying and making of internal cement plastering for walls, consists of 350 kg of Portland cement for cubic meter of sand according to the approved drawings and technical specifications | m2 | 535 | 23 | 54.4 | 0 | 54.4 | 1251.2 |  | 0% | 10.17% |  | 1251.2
3.4.3 | Supplying and making of external smooth render (fetisa), with a required colour, consists of three layers for facades, according to the approved drawings and technical specifications.. | m2 | 135 | 30 | 135 | 0 | 135 | 4050 |  | 25% | 100% | لحين نهو الأعمال | 3037.5
3.4.4 | Supplying and making of external cement skirting with a required colour for facades according to the approved drawings and technical specifications. | m2 | 39 | 28 | 37 | 0 | 37 | 1036 |  | 20% | 94.87% | لحين نهو الأعمال | 828.8
3.5 | Tiles works | [6 empty] | 0
3.5.1 | Supplying and bonding of (muzaiek) tiles with dimensions of 20x20x2 cm for deck roofs. The unit price includes the skirting with height of 20 cm according to the approved drawings and technical specifications. | m2 | 213 | 36 | 213 | 0 | 213 | 7668 |  | 0% | 100% |  | 7668
3.5.2 | Supplying and bonding of friction resistant tiles for floors, thickness not less than 0.8 cm with a required colour according to the approved drawings and technical specifications. | m2 | 215 | 80 | 160 | 0 | 160 | 12800 |  | 5% | 74.42% |  | 12160
3.5.3 | Supplying and bonding of acids resistant ceramic tiles for the internal walls and floors of alum basins, thickness not less than 0.8 cm with a required colour according to the approved drawings and technical specifications. | m2 | 137 | 120 | 137 | 0 | 137 | 16440 |  | 5% | 100% |  | 15618
3.5.4 | Supplying and fixing of oswanic red marble for the steps of stairs according to the approved drawings and technical specifications. | m | 25 | 250 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
3.6 | Internal paints works | [6 empty] | 0
3.6.1 | Supplying, and painting of plastic paints on internal cement plastering for ceiling and walls according to the approved drawings and technical specifications. | m2 | 784 | 20 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
3.7 | wood and cretal works | [6 empty] | 0
3.7.1 | Supplying and fixing of wooden frames from Sweden no 1 type with a section of 2* x 5VV for vents of cretal windows. The unit price includes fixing, painting and all required works to finish the work according to the approved drawings and technical specifications. | m | 96 | 100 | 96 | 0 | 96 | 9600 |  | 0% | 100% |  | 9600
3.7.2 | Supplying and fixing of a cretal window with dimensions of (3.00 m x 1.00 m), consists of 12 moving panels, including 6 mm thickness glass and accessories. The unit price includes fixing and all required works to finish the work according to the approved drawings and technical specifications. | no | 11 | 650 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
3.8 | steel works
3.8.1 | Supplying, manufacturing and fixing of a steel door, with dimensions of (2.50 mx3.10 m), consists of 2 hinged panels, opening on circular rollers in the floor. The unit price includes steel frames, accessories and ironmongery as described. It also includes fixing, welding, painting and all required works to finish the work according to the approved drawings and technical specifications. | kg | 1200 | 13 | 605 | 0 | 605 | 7865 |  | 10% | 50.42% | لحين نهو الأعمال | 7078.5
3.8.2 | Supplying, manufacturing and fixing of a steel door, with dimensions of (1.50 mx2.20 m), consists of one hinged panel, opening inside. The unit price includes steel frames, accessories and ironmongery as described. It also includes fixing, welding, painting and all required works to finish the work according to the approved drawings and technical specifications. | kg | 250 | 12 | 235 | 0 | 235 | 2820 |  | 10% | 94% | لحين نهو الأعمال | 2538
3.8.3 | Supplying, manufacturing and fixing of a steel ladder from steel bars with 25 mm diameter. The unit price includes fixing, welding, painting and all required works to finish the work according to the approved drawings and technical specifications. | no | 4 | 1500 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
3.8.4 | Supplying and construction of inspection vents according to the approved drawings and technical specifications. | no | 1 | 2000 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
3.8.5 | Supplying, manufacturing and fixing of a protection handrail for the stairs, from galvanized steel pipes with 2 inches diameter, without using welding. The unit price includes painting, fixing and all required works to finish the work according to the approved drawings and technical specifications. | m | 12 | 300 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
| المقاول contractor | الاستشارى consultant |  |  |  |  | PIU Manager رئيس وحدة تنفيذ المشروع |  |  |  |  | اجمالي الصفحة | 894600.105
| Signed التوقيع : | Signed التوقيع : |  |  |  | Signed التوقيع :
| Date التاريخ: | Date التاريخ: |  |  |  | Date التاريخ: |  |  |  |  | Chairman رئيس مجلس إدارة الشركة
Signed التوقيع :
Date التاريخ:
| ماقبله | [11 empty] | 894600.105
3.8.6 | Supplying and construction of cables channels, with lengths and dimensions according to the approved drawings. The unit price includes sulphate resistant ceramic for the internal surfaces of the channels, the steel sheets for the covering and the steel frames. It also includes fixing, welding, painting and all required works to finish the work according to the approved drawings and technical specifications. | m | 30 | 1500 | 12.7 | 0 | 12.7 | 19050 |  | 30% | 42.33% | لحين نهو الأعمال | 13335
3.8.7 | Sutrolvine and construction of pipes channels, with lengths and dimensions according to the approved drawings. The unit price includes sulphate resistant ceramic for the internal surfaces of the channels, the steel sheets for the covering and the steel frames. It also includes fixing, welding, painting and all required works to finish the work according to the approved drawings and technical specifications. | m | 20 | 2500 | 10.1 | 0 | 10.1 | 25250 |  | 30% | 50.5% | لحين نهو الأعمال | 17675
3.8.8 | Supplying and construction of wastewater drainage systems (Grailya), according to the approved drawings and technical specifications. | m | 20 | 150 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
3.9 | Rains drainage works: | [6 empty] | 0
3.9.1 | Supplying and fixing of uP.V.C greygory 4 inches for deck roof rain drainage. The unit price includes suppling and fixing of uP.V.C plastic pipes 4 inches diameter, fixed vertically on outside external walls for deck roof rain drainage. It also includes joints, elbows, anchors and all required works to finish the work according to the approved drawings and technical specifications. | no | 1 | 750 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
4 | Chlorine Building Works:
4.1 | Excavation , Filling and Replacement Soil Works: | [6 empty] | 0
4.1.1 | Excavation for the foundation of the building. The unit price includes; a) Excavation up to 3.40 m depth b) Shallow dewatering system by a safe and scientific method that does not effect on neighbors construction stability. c) Transport the results of excavation to the main places that prepared for that. d) Supplying all required machines to finish the work according to the approved drawings and technical specifications. The unit price also includes the filling around foundation by good supplied sands to the average level of ground surface. | m3 | 990 | 50 | 1345.3 | 0 | 1345.3 | 67265 |  | 0% | 135.9% | تم زيادة الكمية طبقا لأمر الشغل رقم 1 | 67265
4-2 | Plain and Reinforced concrete works:
4.2.1 | Supplying and pouring of plain concrete for the foundation consists of 0.8 m3 gravel, 0.4 m3 sand and 250 kg/m3 Portland sulphate resistant cement to get strength (fc2s) not less than 200 kg/cm2 according to the approved drawings and technical specifications. | m3 | 103 | 446 | 108.36 | 0 | 108.36 | 48328.56 |  | 0% | 105.2% | تم زيادة الكمية طبقا لأمر الشغل رقم 1 | 48328.56
4.2.2 | Supplying and construction of plain concrete for floors, with thickness of 10 cm, consists of 0.8 m3 gravel 0.4 m3 sand and 250 kg/m3 of Portland cement, strength (fc28) not less than 200 kg/cm2 according to the approved drawings and technical specifications. | m2 | 160 | 45 | 161.63 | 0 | 161.63 | 7273.35 |  | 0% | 101% | تم زيادة الكمية طبقا لأمر الشغل رقم 1 | 7273.35
4.2.3 | Supplying and construction of plain concrete for floors, with thickness of 15 cm. consists of 0.8 m3 gravel 0.4 m3 sand and 250 kg/m3 of Portland cement, strength (fc28) not less than 200 kg/cm2 according to the approved drawings and technical specifications. | m2 | 160 | 67 | 161.63 | 0 | 161.63 | 10829.21 |  | 0% | 101% | تم زيادة الكمية طبقا لأمر الشغل رقم 1 | 10829.21
4.2.4 | Supplying and construction of a replacement soil under the foundation, from graduated gravel, with a thickness of 50 cm in two layers, including compaction and all required tests according to soil research and foundation report. The unit price includes all required works to finish the work according to the approved drawings and technical specifications. | m3 | 291 | 150 | 291 | 0 | 291 | 43650 |  | 0% | 100% |  | 43650
4.2.5 | Supplying and construction of reinforced concrete for the foundation, consists of 0.8 m3 gravel, 0.4 m3 sand and 400 kg/m3 of Portland sulphate resistant cement, strength (fc2s) not less than 300 kg/cm2 according to approved drawings and technical specifications. | m3 | 65 | 1120 | 66 | 0 | 66 | 73920 |  | 0% | 101.5% | تم زيادة الكمية طبقا لأمر الشغل رقم 1 | 73920
4.2.6 | Supplying and construction of reinforced concrete for columns, ceilings and all reinforced concrete works over the top level of the foundation, consists of 0.8 m3 gravel, 0.4 m3 sand and 350 kg/m3 of Portland cement, strength (fc2s) not less than 300 kg/cm2 according to the approved drawings and technical specifications. | m3 | 97 | 1300 | 121.59 | 0 | 121.59 | 158067 |  | 0% | 125.4% | تم زيادة الكمية طبقا لأمر الشغل رقم 1 | 158067
4.2.7 | Supplying and construction of reinforced concrete fair face, (A) type, for the walls of neutralization tower, consists of 0.8 m3 gravel, 0.4 m3 sand and 400 kg/m3 of Portland sulphate resistant cement, strength (fc28) not less than 300 kg/cm2 according to the approved drawings and technical specifications. | m3 | 10 | 1550 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
4.3 | Insulation Works
4.3.1 | Supplying and laying of water proofing insulation for the reinforced concrete of the foundation to 15 cm above the ground surface, consists of 3 layers of hot oxided bitumen according to the approved drawings and technical specifications. | m2 | 1100 | 25 | 469.49 | 0 | 469.49 | 11737.25 |  | 0% | 42.68% |  | 11737.25
4.3.2 | Supplying and making of water proofing coating consists of one layer of insuplast non - woven polyester for deck roofs, floors and path rooms. The unit price includes all required works to finish the work according to the approved drawings and technical specifications. | m2 | 295 | 65 | 501.4 | 0 | 501.4 | 32591 |  | 0% | 170% | تم زيادة الكمية طبقا لأمر الشغل رقم 1 | 32591
4.3.3 | Supplying and making of a heat insulation layer, for deck roofs, from polyethylene foam 5 cm thickness. The unit price includes all required works to finish the work according to the approved drawings and technical specifications. | m2 | 185 | 85 | 275.99 | 0 | 275.99 | 23459.15 |  | 0% | 149.2% | تم زيادة الكمية طبقا لأمر الشغل رقم 1 | 23459.15
4.3.4 | Supplying and construction of plain concrete (7 cm average thickness) for deck roofs. The unit price includes the slopes and all required works to finish the work according to the approved drawings and technical specifications. | m2 | 185 | 32 | 275.99 | 0 | 275.99 | 8831.68 |  | 0% | 149.2% | تم زيادة الكمية طبقا لأمر الشغل رقم 1 | 8831.68
| المقاول contractor | الاستشارى consultant |  |  |  | PIU Manager رئيس وحدة تنفيذ المشروع | [5 empty] | اجمالي الصفحة | 1411562.305
| Signed التوقيع : | Signed التوقيع : |  |  |  | Signed التوقيع :
| Date التاريخ: | Date التاريخ: |  |  |  | Date التاريخ: |  |  |  |  | Chairman رئيس مجلس إدارة الشركة
Signed التوقيع :
Date التاريخ:
| ماقبله | [11 empty] | 1411562.305
4.3.5 | Supplying and construction of plain concrete for entrance ramps with light reinforcements (6 <5 6 mm/mv in both direction) consists of 0.8 m3 gravel, 0.4 m3 sand and 250 kgm/m3 of Portland sulphate resistant cement according to the approved drawings and technical specifications. | m2 | 5 | 150 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
4.4 | Brick wall works | [6 empty] | 0
4.4.1 | Supplying and construction of (tafly) brick walls with dimensions of 25x12x6 cm, the cement content in the used mortar is 350 kg for cubic meter of sand, according to the approved drawings and technical specifications. | m3 | 15 | 400 | 9.92 | 0 | 9.92 | 3968 |  | 0% | 66.13% |  | 3968
4.4.2 | fDrg.No.O") and f4) Class.Arch.) Supplying and construction of sand brick walls with dimensions 25x12x6 cm for external walls of the building. The cement content in used mortar is 350 kg for cubic meter of sand, according to the approved drawing and technical specifications. | m3 | 50 | 600 | 46.23 | 0 | 46.23 | 27738 |  | 10% | 92.46% | لحين نهو الاعمال | 24964.2
4.4.3 | Supplying and construction of cement brick walls 25x12x6 cm. The cement content in used mortar is 350 kg of Portland sulphate resistant cement for each cubic meter of sand according to the approved drawings and technical specifications | m3 | 18 | 400 | 30.6 | 0 | 30.6 | 12240 |  | 0% | 170% | تم زيادة الكمية طبقا لأمر الشغل رقم 1 | 12240
4.4.4 | Supplying and construction of cement brick walls with a thickness of 12 cm for the protection of outside water proofing layer of the reinforced concrete walls for the neutralization solution tank under ground. The cement content in used mortar is 350 kg of Portland sulphate resistant cement for each cubic meter of sand, according to the approved drawings and technical specifications | m2 | 30 | 50 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
4.5 | finishing works
4.5.1 | Supplying and making of internal cement plastering for ceilings, consists of 350 kg of Portland cement for each cubic meter of sand, according to the approved drawings and technical specifications. | m2 | 180 | 23 | 345.9 | 0 | 345.9 | 7955.7 |  | 5% | 192.2% | تم زيادة الكمية طبقا لأمر الشغل رقم 1 | 7557.915
4.5.2 | Supplying and making of external cement skirting with a required colour for facades according to the approved drawings and technical specifications. | m2 | 33 | 28 | 26.87 | 0 | 26.87 | 752.36 |  | 30% | 81.42% | لحين نهو الاعمال | 526.652
4.5.3 | Supplying and making of internal cement plastering for walls, consists of 350 kg of Portland cement for each cubic meter of sand, according to the approved drawings and technical specifications | m2 | 100 | 25 | 173.28 | 0 | 173.28 | 4332 |  | 5% | 173.3% | تم زيادة الكمية طبقا لأمر الشغل رقم 1 | 4115.4
4.5.4 | Supplying and making of external smooth render (fetisa), with a required colour, consists of three layers for facades, according to the approved drawings and technical specifications.. | m2 | 122 | 30 | 261.28 | 0 | 261.28 | 7838.4 |  | 30% | 214.2% | تم زيادة الكمية طبقا لأمر الشغل رقم 1 | 5486.88
4.6 | Tiles Works: | [6 empty] | 0
4.6.1 | Supplying and bonding of (muzaiek) tiles with dimensions of 20 x 20 x 2 cm for deck roofs. The unit price includes the skirting with height of 20 cm according to the approved drawings and technical specifications. | m2 | 185 | 36 | 275.99 | 0 | 275.99 | 9935.64 |  | 20% | 149.2% | تم زيادة الكمية طبقا لأمر الشغل رقم 1 | 7948.512
4.6.2 | Supplying and bonding of friction and acids resistant ceramic tiles for floors, thickness not less than 0.8 cm, according to the approved drawings and technical specifications. | m2 | 110 | 80 | 110 | 0 | 110 | 8800 |  |  | 100% |  | 8800
4.6.3 | Supplying and bonding of acids resistant ceramic tiles for walls, thickness not less than 0.8 cm with a required colour according to the approved drawings and technical specifications. | m2 | 145 | 120 | 145 | 0 | 145 | 17400 |  |  | 100% |  | 17400
4.6.4 | Supplying and fixing of oswanic red marble for the steps of stairs according to the approved drawings and technical specifications. | m | 10 | 200 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
4.7 | Internal paints works
4.7.1 | Supplying, and painting of plastic paints on the internal cement plastering for ceilings and walls according to the approved drawings and technical specifications. | m2 | 275 | 20 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
4.8 | wood works | [5 empty] | 0 | 0
4.8.1 | Supplying and fixing of wooden frames from Sweden no 1 type with a section of 2* x 5VV for alumetal windows. The unit price includes fixing, painting and all required works to finish the work according to the approved drawings and technical specifications. | m | 165 | 100 | 79.4 | 0 | 79.4 | 7940 |  | 0% | 48.12% |  | 7940
4.8.2 | Supplying and fixing of a hinged wooden door, consists of one panel, opening inside, with dimensions of (1.00 m x 2.20 m), including the wooden frames, accessories, painting and all required works to finish the work according to the approved drawings and technical specifications. | no | 3 | 1000 | 3 | 0 | 3 | 3000 |  | 40% | 100% | لحين نهو الاعمال | 1800
4.9 | Alumetal works
4.9.1 | Supplying and fixing of an alumetal window with dimensions of (3.50 m x 1.50 m), including 6 mm thickness glass and accessories, consists of 12 moving panels on a horizontal track. The unit price includes all required works to finish the work according to the approved drawings and technical specifications. | no | 4 | 2625 | 4 | 0 | 4 | 10500 |  | 5% | 100% |  | 9975
4.9.2 | Supplying and fixing of an alumetal window with dimensions of (3.00 m x 1.20 m), including 6 mm thickness glass and accessories, consists of 3 sliding panels on a horizontal track. The unit price includes all required works to finish the work according to the approved drawings and technical specifications. | no | 2 | 1800 | 1 | 0 | 1 | 1800 |  | 5% | 50% |  | 1710
4.9.3 | Supplying and fixing of an alumetal window with dimensions of (2.00 m * 1.50 m), including 6 mm thickness glass and accessories, consists of 21 moving panels on a horizontal track. The unit price includes all required works to finish the work according to the approved drawings and technical specifications. | no | 3 | 1500 | 3 | 0 | 3 | 4500 |  | 5% | 100% |  | 4275
4.9.4 | Supplying and fixing of an alumetal window with dimensions of (2.00 m x 1.20 m), including 6 mm thickness glass and accessories, consists of 3 sliding panels on a horizontal track. The unit price includes all required works to finish the work according to the approved drawings and technical specifications. | no | 2 | 1200 | 2 | 0 | 2 | 2400 |  | 5% | 100% |  | 2280
| المقاول contractor | الاستشارى consultant |  |  |  | PIU Manager رئيس وحدة تنفيذ المشروع | [5 empty] | اجمالي الصفحة | 1532549.864
| Signed التوقيع : | Signed التوقيع : |  |  | Signed التوقيع :
| Date التاريخ: | Date التاريخ: |  |  | Date التاريخ: |  |  |  |  | Chairman رئيس مجلس إدارة الشركة
Signed التوقيع :
Date التاريخ:
| ماقبله | [11 empty] | 1532549.864
4.10 | steel works
4.10.1 | Supplying, manufacturing and fixing of (two) hinged steel doors, with dimensions of (3.50 m x 3.00 m), consists of two panels, opening on circular rollers in the floor. The unit price includes steel frames and accessories. It also includes fixing, welding, painting and all required works to finish the work according to the approved drawings and technical specifications. (2 doors x 700 kg) | kg | 1400 | 13 | 1080 | 0 | 1080 | 14040 |  | 10% | 77.14% | لحين نهو الاعمال | 12636
4.10.2 | Supplying and making of a ventilation vent with dimensions of (3.50 mx 0.50 m), including wooden frames 2* x 5* from Sweden no (1) type. It also includes steel bars, painting and all required works to finish the work according to the approved drawings and technical specifications. | no | 4 | 4000 | 4 | 0 | 4 | 16000 |  | 0% | 100% |  | 16000
4.10.3 | Supplying and making of a ventilation vent with dimensions of (3.00 m* 0.50 m), including wooden frames 2* x 5* from Sweden no (1) type. It also includes steel bars, painting and all required works to finish the work according to the approved drawings and technical specifications. | no | 3 | 3600 | 2 | 0 | 2 | 7200 |  | 0% | 66.67% |  | 7200
4.10.4 | Supplying and making of a ventilation vent with dimensions of C2.00 mx 0.50 m), including wooden frames 2* x 5* from Sweden no (1) type. It also includes steel bars, painting and all required works to finish the work accordingto the approved drawings and technical specifications. | no | 2 | 2500 | 2 | 0 | 2 | 5000 |  | 0% | 100% |  | 5000
4.10.5 | Supplying, manufacturing and fixing of a steel ladder from steel bars with 25 mm diameter. The unit price includes fixing, welding, painting and all required works to finish the work accordingto the approved drawings and technical specifications. | no | 2 | 2000 | 1 | 0 | 1 | 2000 |  | 0% | 50% |  | 2000
4.11 | Sanitary works
4.11.1 | Supplying and fixing of uP.V.C greygory 4 inches diameter, for deck roof rain drainage. The unit price includes all required works to finish the work according to the approved drawings and technical specifications. | no | 4 | 350 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
4.11.2 | Supplying and making of wastewater drainage systems (Grailya) for the chlorine building, according to the approved drawings and technical specifications. | m | 32 | 150 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
4.11.3 | Supplying and construction of cables channels. The unit price includes all required works to finish the work according to the approved drawings and technical specifications. | m | 20 | 1500 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
4.11.4 | Supplying and fixing of U.P.V.C plastic pipes 4 inches diameter, Fixed vertically on outside external walls, for deck roof rains drainage. The unit price includes joints, elbows, anchors and all required works to finish the work according to the approved drawings and technical specifications. | m | 7 | 100 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
5 | Generator building
5.1 | Excavation and replacment work
5.1.1 | Excavation for the foundation of the building. The unit price includes; a) Excavation up to 2.40 m depth b) Shallow dewatering system by a safe and scientific method that does not effect on neighbors construction stability. c) Transport the results of excavation to the main places that prepared for that. d) Supplying all required machines to finish the work according to the approved drawings and technical specifications. The unit price also includes the filling around foundation by good supplied sands to the average level of ground surface. | m3 | 180 | 32 | 200.34 | 0 | 200.34 | 6410.88 |  | 0% | 111.3% | تم زيادة الكمية طبقا لأمر الشغل رقم 2 | 6410.88
5.1.2 | Supplying and construction of a replacement soil under the foundation, from good supplied sands, in layers, the thickness of each layer should not be less than 25 cm, including compaction and all required tests according to soil research and foundation report. The unit price includes all required works to finish the work according to the approved drawings and technical specifications. | m3 | 75 | 55 | 83.74 | 0 | 83.74 | 4605.7 |  | 0% | 111.7% | تم زيادة الكمية طبقا لأمر الشغل رقم 2 | 4605.7
5.2 | Plain and Reinforced concrete works
5.2.1 | Plain and Reinforced concrete works: (Section 2.2.3.8 of general civil specification) (Drg.No.(4) Class.Str.) Supplying and pouring of plain concrete for the foundation consists of 0.8 m3 gravel, 0.4 m3 sand and 250 kg/m3 Portland sulphate resistant cement to get strength (fc2s) not less than 200 kg/cm2 according to the approved drawings and technical specifications. | m3 | 24 | 446 | 26.41 | 0 | 26.41 | 11778.86 |  | 0% | 110% | تم زيادة الكمية طبقا لأمر الشغل رقم 2 | 11778.86
5.2.2 | Supplying and construction of plain concrete for floors, with thickness of 10 cm, consists of 0.8 m3 gravel, 0.4 m3 sand and 250 kg/m3 of Portland cement, strength (fc28) not less than 200 kg/cm2 according to the approved drawings and technical specifications. | m2 | 33 | 45 | 21.65 | 0 | 21.65 | 974.25 |  | 10% | 65.61% | لحين ورود شهادات تكسير المكعبات | 876.825
5.2.3 | Supplying and construction of plain concrete for floors, with thickness of 15 cm, consists of 0.8 m3 gravel, 0.4 m3 sand and 250 kg/m3 of Portland cement, strength (fc28) not less than 200 kg/cm2 according to the approved drawings and technical specifications. | m2 | 33 | 67 | 21.65 | 0 | 21.65 | 1450.55 |  | 10% | 65.61% | لحين ورود شهادات تكسير المكعبات | 1305.495
5.2.4 | Supplying and construction of plain concrete (7 cm average thickness) for deck roofs, including the slopes and all required works to finish the work according to the approved drawings and technical specifications. | m2 | 44 | 32 | 45.14 | 0 | 45.14 | 1444.48 |  | 0% | 102.6% | تم زيادة الكمية طبقا لأمر الشغل رقم 2 | 1444.48 | v.o
5.2.5 | Supplying and construction of plain concrete for entrance ramps with light reinforcements 608 mm/rf in both direction, consists of 0.8 m3 gravel, 0.4 m3 sand and 250 kgm/m3 of Portland sulphate resistant cement according to the approved drawings and technical specifications. | m2 | 3 | 140 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
| المقاول contractor | الاستشارى consultant |  |  |  |  | PIU Manager رئيس وحدة تنفيذ المشروع |  |  |  |  | اجمالي الصفحة | 1601808.104
| Signed التوقيع : | Signed التوقيع : |  |  |  | Signed التوقيع :
| Date التاريخ: | Date التاريخ: |  |  |  | Date التاريخ:
Chairman رئيس مجلس إدارة الشركة
Signed التوقيع :
Date التاريخ:
| ماقبله | [11 empty] | 1601808.104
5.2.6 | Supplying and pouring of plain concrete for the generator base, consists of 0.8 m3 gravel, 0.4 m3 sand and 300 kg/m3 Portland cement, with light reinforcement according to the approved drawings and technical specifications. | l.s | 1 | 1500 | 1 | 0 | 1 | 1500 |  | 0% | 100% |  | 1500
5.2.7 | Supplying and construction of reinforced concrete for the foundation consists of 0.8 m3 gravel, 0.4 m3 sand and 400 kg/m3 of Portland sulphate resistant cement, strength (fc2s) not less than 300 kg/cm2 according to the approved drawings and technical specifications. | m3 | 15 | 1175 | 12 | 0 | 12 | 14100 |  | 0% | 80% |  | 14100
5.2.8 | Supplying and construction of reinforced concrete for columns, ceilings and all reinforced concrete works over the top level of the foundation, consists of 0.8 m3 gravel, 0.4 m3 sand and 350 kg/m3 of Portland cement to get strength (fc2s) not less than 300 kg/cm2 according to the approved drawings and technical specifications. | m3 | 15 | 1300 | 27.5 | 0 | 27.5 | 35750 |  | 0% | 183.3% | تم زيادة الكمية طبقا لأمر الشغل رقم 2 | 35750
5.3 | Insulation Works
5.3.1 | Supplying and laying of water proofing insulation for the reinforced concrete of the foundation to 15 cm above the ground surface, consists of 3 layers of hot oxided bitumen according to the approved drawings and technical specifications. | m2 | 40 | 23 | 85.72 | 0 | 85.72 | 1971.56 |  | 0% | 214.3% | تم زيادة الكمية طبقا لأمر الشغل رقم 2 | 1971.56
5.3.2 | Supplying and making of water proofing coating consists of one layer of insuplast non - woven polyester for deck roofs and floors. The unit price includes all required works to finish the work according to the approved drawings and technical specifications. | m2 | 44 | 65 | 66.54 | 0 | 66.54 | 4325.1 |  | 0% | 151.2% | تم زيادة الكمية طبقا لأمر الشغل رقم 2 | 4325.1 | v
5.3.3 | Supplying and making of a heat insulation layer, for deck roofs, from polyethylene foam 5 cm thickness. The unit price includes all required works to finish the work according to the approved drawings and technical specifications. | m2 | 44 | 85 | 44.89 | 0 | 44.89 | 3815.65 |  | 0% | 102% | تم زيادة الكمية طبقا لأمر الشغل رقم 2 | 3815.65 | v
5.4 | Brick wall works
5.4.1 | Supplying and construction of (tafly) brick walls 25x12x6 cm. The cement content in used mortar is 350 kg of Portland cement for each cubic meter of sand according to the approved drawings and technical specifications | m3 | 4 | 400 | 5.74 | 0 | 5.74 | 2296 |  | 0% | 143.5% | تم زيادة الكمية طبقا لأمر الشغل رقم 2 | 2296 | v
5.4.2 | Supplying and construction of sand brick walls with with dimensions 25x12x6 cm for external walls of the building, according to the approved drawing and technical specifications. | m3 | 19 | 600 | 15 | 0 | 15 | 9000 |  | 0% | 78.95% |  | 9000
5.5 | finishing works
5.5.1 | Supplying and making of cement plastering for internal walls and ceilings, consists of 350 kg of Portland cement for each cubic meter of sand according to the approved drawings and technical specifications. | m2 | 80 | 25 | 40 | 0 | 40 | 1000 |  | 0% | 50% |  | 1000
5.5.2 | Supplying and making of external smooth render (fetisa), with a required colour, consists of three layers for facades, according to the approved drawings and technical specifications. | m2 | 66 | 30 | 109.48 | 0 | 109.48 | 3284.4 |  | 20% | 165.9% | تم زيادة الكمية طبقا لأمر الشغل رقم 2 | 2627.52
5.5.3 | Supplying and making of external cement skirting with a required colour for facades, according to the approved drawings and technical specifications. | m2 | 15 | 28 | 10 | 0 | 10 | 280 |  | 20% | 66.67% | لحين نهو الأعمال | 224
5.6 | Internal paints works
5.6.1 | Supplying, and painting of plastic paints on the internal cement plastering for ceiling and walls according to the approved drawings and technical specifications. | m2 | 80 | 20 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
5.7 | tiles works | [6 empty] | 0
5.7.1 | (Section 2.2.3.15 of general civil specification) (Drg.No.(7) Class.Arch) Supplying and bonding of cement tiles with dimensions of 20 x 20 x 2 cm for deck roofs. The unit price includes the skirting with height of 20 cm according to the approved drawings and technical specifications. | m2 | 66 | 25 | 43.85 | 0 | 43.85 | 1096.25 |  | 0% | 66.44% |  | 1096.25
5.8 | steel works | [6 empty] | 0
5.8.1 | Supplying, manufacturing and fixing of a steel door, with dimensions of (3.00m x 4.10m), consists of two hinged panels, moving on circular rollers in the floor. The unit price includes steel frames and accessories. It also includes welding, painting and all required works to finish the work according to the approved drawings and technical specifications. | kg | 900 | 13 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
5.9 | crital works:
5.9.1 | Supplying and fixing of a crital window with dimensions of (3.50m x 1.00m), consists of 14 moving panels on a horizontal axis, including 6 mm thickness glass and accessories. The unit price includes, supplying and fixing of wooden frames from Sweden no 1 type with a section of 2\\ * 5\\ including its painting. It also includes all required works to finish the work according to the approved drawings and technical specifications. | no | 1 | 1400 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
5.9.2 | Supplying and fixing of a crital window with dimensions of (3.50m x 1.40m), consists of 7 fixed panels, including 6 mm thickness glass and accessories. The unit price includes, supplying and fixing of wooden frames from Sweden no 1 type with a section of 2\\ x 5\\ including its painting. It also includes all required works to finish the work according to the approved drawings and technical specifications. | no | 1 | 2000 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
5.9.3 | Supplying and fixing of a crital window with dimensions of (3.00m x 1.50m), consists of 6 fixed panels, including 6 mm thickness glass and accessories. The unit price includes, supplying and fixing of wooden frames from Sweden no 1 type with a section of 2\\ x 5\\ including its painting. It also includes all required works to finish the work according to the approved drawings and technical specifications. | no | 1 | 1800 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
5.9.4 | Supplying and fixing of a crital window with dimensions of (1.50m x 1.00m), consists of 6 moving panels on a horizontal axis, including 6 mm thickness glass and accessories. The unit price includes, supplying and fixing of wooden frames from Sweden no 1 type with a section of 2\\ x 5\\ including its painting. It also includes all required works to finish the work according to the approved drawings and technical specifications. | no | 3 | 600 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
| المقاول contractor | الاستشارى consultant |  |  |  |  | PIU Manager رئيس وحدة تنفيذ المشروع |  |  |  |  | اجمالي الصفحة | 1679514.184
| Signed التوقيع : | Signed التوقيع : |  |  |  | Signed التوقيع :
| Date التاريخ: | Date التاريخ: |  |  |  | Date التاريخ: |  |  |  | Chairman رئيس مجلس إدارة الشركة
Signed التوقيع :
Date التاريخ:
| ما قبله | [11 empty] | 1679514.184
5.10 | Sanitary works
5.10.1 | Supplying and fixing of uP.V.C greygory 4 inches diameter, for deck roof rain drainage. The unit price includes supplying and fixing of u.P.V.C plastic pipes 4 inches diameter, Fixed vertically on outside external walls for deck roof rains drainage. It also includes joints, elbows, anchors and all required works to finish the work according to the approved drawings and technical specifications. | no | 1 | 750 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
6 | raw water rising main pipe line
6.1 | The first alternative : The ductile cast iron Supplying, transporting, installing, testing, washing and disinfection of ductile F-iron pipe lines, (k9 type). The unit price includes:- a) Excavation in all kinds of soil to the required level except rock soil. b) Supporting of the excavation sides. c) Dewatering works by using of safe and suitable method. d) Supplying and construction of a base layer (bedding) under the pipe line with the full breadth of the excavation channel, according to recommendations and conditions of the producercompany for each kind of pipes. e) Supplying and construction of filling soil around the pipe line and over the crest point of its cross-section with a distance not less than 30 cm according to recommendations and conditions of the producer company for each kind of pipes. f) Then, the contractor should complete the filling by using of excavation resulted clean soil in layers according to the technical specifications. g) The contractor must return the pavement layers, levels and final surfaces of roads as they were before, according to the conditions of roads organization. h) Transporting of the excavation results to the main places which prepared for that. i) All internal and external protection works for road guide boards and pipe lines, including their fittings according to technical specifications and conditions of roads organization. j) The following notes must be considered by the contractor since the beginning ; I- the operation pressure of the pipe line will be 60 ms. II- the test pressure of the pipe line will be 90 ms. k) The unit price also includes all required works, equipments and machines to finish the work completely, according to the approved drawings, technical specifications and the conditions of roads organization. ■ Diameter of 1000 mms | m | 3930 | 4850 | 3830 | 100 | 3930 | 19060500 |  | 1% | 100% | تعلية 10% لكمية 130م.ط مواسير لحين ورود شهادة إحتبار الهيئة القومية | 18806845
|  |  | 5 | 42400 | 2 |  | 2 | 84800 |  | 0.1 | 40% | لحين ورود شهادات الاختبار
6.3 | Valves Supplying, transporting, fixing, experiment and testing, of the required valves according to the approved drawings, technical specifications and conditions of the contract. The unit price includes:- a The internal and external protection of the valves. b)The concrete supports under the valves. c) The shown glands in the ceilings of the valves chambers d) Tee-keys for closing and opening purposes of the valves (equal 20 % of each kind number of butterfly valves and sluice valves) e) The unit price of the hidden valves includes supplying and fixing of the above ground box including its all contents and connection pieces from the same kind of th pipes for each alternative.
6.3.1 | Gate valves: ■ Butterfly valves with a manual wheel gearbox (diameter of 1000 mms) ■ | no | 5 | 42400 | 3 | 0 | 3 | 127200 |  | 5% | 60% | لحين التشغيل | 120840
| Butterfly valves with a manual wheel gearbox (diameter of 250 mms) | no | 5 | 3200 | 3 | 0 | 3 | 9600 |  | 5% | 60% | لحين التشغيل | 9120
6.3.2 | Air valves: including the gate valve under the air valve without Tee-pieces (diameter of 200 mms) | no | 2 | 5300 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
6.4 | Fittings (Inside valves chambers) Supplying, transporting, fixing and experiment of the fittings which be shown later, from the same kind of the pipes for each alternative. The unit price includes the internal and external protection of the fittings. It also includes the concrete supports and all required works to finish the work according to the approved drawings, technical specifications and conditions of the contract.
6.4.1 | Tee pieces: ■ Diameter of (1000/ 250) mms | no | 5 | 21300 | 5 | 0 | 5 | 106500 |  | 5% | 100% | لحين التشغيل | 101175
6.4.2 | Puddle pieces (3 flanges pipe): ■ Diameter of (1000) mms ■ | no | 14 | 21300 | 10 | 0 | 10 | 213000 |  | 5% | 71.43% | لحين التشغيل | 202350
| Diameter of (250) mms | no | 5 | 2900 | 3 | 0 | 3 | 8700 |  | 5% | 60% | لحين التشغيل | 8265
6.4.3 | Dismantling pieces: ■Diameter of (1000) mms | no | 5 | 14200 | 3 | 0 | 3 | 42600 |  | 5% | 60% | لحين التشغيل | 40470
| ■ Diameter of (250) mms | no | 5 | 1600 | 3 | 0 | 3 | 4800 |  | 5% | 60% | لحين التشغيل | 4560
6.4.4 | Washing branch: ■ Diameter of (250) mms | no | 5 | 10000 | 3 | 0 | 3 | 30000 |  | 5% | 60% | لحين التشغيل | 28500
6.4.5 | Elbows : ■ An elbow 90° with a diameter of (1000) mms ■ | no | 8 | 26000 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
| An elbow 45° with a diameter of (1000) mms | no | 12 | 20000 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
6.5 | Valves chambers
6.5.1 | Excavation in all kinds of soil to the required level, except the rock soil. The unit price includes transporting of the excavation results to the nearest place which limited by the owner, supporting of the excavation sides and dewatering works if it is required by using of safe and suitable method according to the approved drawings, technical specifications. | m3 | 681 | 60 | 194.82 | 0 | 194.82 | 11689.2 |  | 0% | 28.61% |  | 11689.2
| المقاول contractor | الاستشارى consultant |  |  |  | PIU Manager رئيس وحدة تنفيذ المشروع | [5 empty] | اجمالي الصفحة | 21013328.384
| Signed التوقيع : | Signed التوقيع : |  |  | Signed التوقيع :
| Date التاريخ: | Date التاريخ: |  |  | Date التاريخ: |  |  |  |  | Chairman رئيس مجلس إدارة الشركة
Signed التوقيع :
Date التاريخ:
| ما قبله | [11 empty] | 21013328.384
6.5.2 | Supplying and pouring of plain concrete for the foundation, consists of 0.8 m3 gravel, 0.4 m3 sand and 250 kg/m3 Portland sulphate resistant cement to get strength (fc2s) not less than 200 kg/cm2 according to the approved drawings and technical specifications | m3 | 37 | 450 | 15.22 | 0 | 15.22 | 6849 |  | 10% | 41.14% | لحين ورود شهادات تكسير المكعبات ونهو الأعمال | 6164.1
6.5.3 | Supplying and construction of reinforced concrete for the foundations, walls and ceilings of the valves chambers consists of 0.8 m3 gravel, 0.4 m3 sand and 350 kg/m3 of Portland sulphate resistant cement, with steel reinforcement according to the approved drawings, strength (fc28)not less than 300 kg/cm2 according to technical specifications. | m3 | 190 | 1200 | 50 | 0 | 50 | 60000 |  | 10% | 26.32% | لحين ورود شهادات تكسير المكعبات ونهو الأعمال | 54000
6.5.4 | Supplying and painting of hot oxided bitumen for all outside surfaces of the valves chambers, 3 layers, to the top level of the ceiling, according to the approved drawings and technical specifications. | m2 | 487 | 23 | 107.22 | 0 | 107.22 | 2466.06 |  | 0% | 22.02% |  | 2466.06
6.5.5 | Supplying, manufacturing and fixing of GRC covers, with a diameter of 76 cm and a total weight of 350 kg including the cover frame. The contractor should submit the test certificate. The unit price includes all required works to finish the work according to the approved drawings and technical specifications. | no | 12 | 800 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
6.5.6 | Supplying, manufacturing and fixing of a steel ladder, from steel bars 25 mm diameter, painted by using of an approved E-poxy material. The unit price includes fixing, welding, painting and all required works to finish the work according to the approved drawings and technical specifications. | no | 12 | 4000 | 0 | 6 | 6 | 24000 |  | 0% | 50% |  | 24000
6.6 | crossing works
Supplying and construction of raw water rising main pipe line crossing works for the extensions of the old existing water purification plant in Damietta city with a diameter of 1000mm from the ductile cast-iron. The final length of the crossing works will be limited according to preview record in the presence of the consultant engineer, the owner and the contractor. The unit price includes:- a) The crossing bridge, steel works, piles works and the required permissions. b) All the fittings and required supports. c) The chamber of gate valve before the crossing work consists of the plain and reinforced concrete, steel ladders, covers, outside insulation, internal plastering, floor slope concrete, concrete supports for valves and pipes, fittings, puddle pieces, the gate valve with the same diameter of the rising main pipe line, dismantling pieces and all required works for the chamber operating. d) The air valve of the rising main pipe line above the crossing work with a diameter of 200mm including the gate valve below it and a galvanized steel box for the air valve. e) The contractor must make the required borings to determine the depth of piles and submit the structural and hydraulic design of the crossing work, including the design calculations report and all required drawings for the construction according to the Egyptian code and the ministry of water recourses and irrigation conditions. f) The length of the pipe line will start from the valves chamber to 5m after the end of the crossing work. ■ The contractor must construct any additional works if the consultant and the owner considered those additional works very necessary without any increasing of the prices. ■ The contractor must submit the essential drawings for the crossing work and he also must submit a list of all works for each item of lump summation items which the prices will be limited according to those works
6.6.1 | El-Qanah canal : with a breadth of 35m | L.S. | 1 | 2215000 | 1 | 0 | 1 | 2215000 |  | 10% | 100% | لحين نهو الأعمال | 1993500
6.6.2 | A canal :with a breadth of 10m | L.S. | 1 | 770000 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
6.6.3 | A canal :with a breadth of 8m | L.S. | 1 | 616000 | 1 | 0 | 1 | 616000 |  | 20% | 100% | لحين نهو الأعمال | 492800
6.7 | variable works
6.7.1 | Changing of water pipes paths until 4 inches diameter which object the rising main pipe line of raw water. The unit price includes: - a) Opening and fixing of the water pipe lines in their new paths. b) Excavation and filling with good supplied sands under the water pipe line with a thickness of 20 cm and 20 cm thickness also over the crest point of the pipe line cross section. c) All the fittings, pipes and required connection pieces according to the kinds of pipes for the fixing and operating in order to return the thing to its original case according to specifications. d)The expenses of licenses and all required works for operating the water pipe line according to technical specifications and conditions of the contract. | m | 100 | 200 | 100 | 0 | 100 | 20000 |  | 0% | 100% |  | 20000
6.7.2 | Breaking of the rock soil which objects the excavation works of the raw water rising main pipe line. The contractor must submit the required approved engineering reports according to technical specifications and conditions of the contract. | m3 | 50 | 60 | 50 | 0 | 50 | 3000 |  | 0% | 100% |  | 3000
miscellaneous works
| Excavation and filling works: | [6 empty] | 0
1.1 | Excavation for the foundation of the building, in rock soil (if any). | m3 | 10 | 60 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
1.2 | Supporting of the excavation sides (if any) for the required depths according to the supervisor instructions. And the contractor shall submit atechnical report for the proposed supporting works to be approved by the supervising consultant. | m | 200 | 1500 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
1.3 | Deep dewatering system by using a safe and scientific method that does not effect on neighbors constructions stability according to the supervisor instructions. And the contractor shall submit atechnical report for the proposed deep dewatering to be approved by the supervising consultant. | day | 28 | 37000 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
| المقاول contractor | الاستشارى consultant |  |  |  | PIU Manager رئيس وحدة تنفيذ المشروع | [5 empty] | اجمالي الصفحة | 23609258.544
| Signed التوقيع : | Signed التوقيع : |  |  | Signed التوقيع :
| Date التاريخ: | Date التاريخ: |  |  | Date التاريخ: |  |  |  |  | Chairman رئيس مجلس إدارة الشركة
Signed التوقيع :
Date التاريخ:
| ما قبله | [11 empty] | 23609258.544
Mechanical Works
Table No. (1) The equipment of raw water intake equipment
Supply, erection, testing and delivery in good working condition according to technical specifications and drawings for the following items
1 | screens As shown in drawing and mechanical specification. | L.S | 1 | 5400 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
2 | Monorail crane for foot valve and screen As shown in drawing and mechanical specification. | No. | 1 | 37260 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
3 | Fixed Steel bridge with its pills as shown in drawing and handrails. As shown in drawing and mechanical specification. | L.S | 1 | 910000 | 85% | 0% | 85% | 773500 |  | 0% | 85% |  | 773500
4 | foot valve (f> . As shown in drawing and mechanical specification. | No. | 3 | 57500 | 3 | 0 | 3 | 172500 |  | 0% | 100% |  | 172500
5 | All pump suction pipes from Nil Revir up to pumps with diameter of 700 mm and all accessories. | L.S | 1 | 617000 | 100% | 0% | 100% | 617000 |  | 5% | 100% | لحين التشغيل | 586150
| Table No. (2) Raw water pumping station equipment | [11 empty] | 0
Supply, erection, testing and delivery in good working condition according to technical specifications and drawings for the following items
1 | Raw water pumping unit for new intake 600 Lit/sec at 30 ms head complete with driving motors. As shown in drawing and mechanical specification. | No. | 3 | 223500 | 3 | 0 | 3 | 670500 |  | 10% | 100% | لحين التشغيل | 603450
2 | Suction pipes with all accessories complete with valves, and delivery pipes complete with non-return and shut-off valves for water pumps for 600 Lit/sec pumps As shown in drawing and mechanical specification. | No. | 3 | 140500 | 3 | 0 | 3 | 421500 |  | 20% | 100% | لحين ورود شهادة الإختبار وتوريد مشغلات المحابس 600مم | 337200
3 | Main delivery pipe with all accessories with valves and accessories for RAW water pumps (up to out side the pump room one water) As shown in drawing and mechanical specification. | L.S | 1 | 142000 | 1 | 0 | 1 | 142000 |  | 10% | 100% | لحين التشغيل | 127800
4 | Priming system with all accessories (pipes , valves,....) As shown in drawing and mechanical specification. | L.S | 1 | 443000 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
5 | magnetic flow meter As shown in drawing and mechanical specification. | L.S | 1 | 274400 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
6 | Water hammer equipments as shown in drawing and mechanical specification. | L.S | 1 | 515000 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
Table No, (3) Treated water pumping station equipment
Supply, erection, testing and delivery in good working condition according to technical specifications and drawings for the following items
1 | Treated water pumping unit 500 Lit/sec at 60 ms head complete with driving motors and all accessories As shown in drawing and mechanical specification. | No. | 3 | 517500 | 0 | 3 | 3 | 1552500 |  | 10% | 100% | لحين التشغيل | 1397250
2 | Suction pipes with all accessories complete with valves, and delivery pipes complete with non-return and shut-off valves for 500 Lit/sec pumps As shown in drawing and mechanical specification. | No. | 3 | 158500 | 3 | 0 | 3 | 475500 |  | 50% | 100% | لحين نهو الأعمال | 237750
3 | Main delivery pipe with all accessories with valves and accessories for treated water pumps (up to out side the pump room ) As shown in drawing and mechanical specification. | L.S | 1 | 204000 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
4 | magnetic flow meter As shown in drawing and mechanical specification. | L.S | 1 | 216000 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
5 | Water hammer equipments as shown in drawing and mechanical specification. | L.S | 1 | 355500 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
Table No. (4) Chemical house equipment and Chlorination house equipment
Supply, erection, testing and delivery in good working condition according to technical specifications and drawings for the following items
1 | Alum injecting system equipment As shown in drawing and mechanical specification. | L.S | 1 | 706000 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
2 | Chlorination system equipment As shown in drawing and mechanical specification. | L.S | 1 | 1288900 | 1 | 0 | 1 | 1288900 |  | 25% | 100% | لحين نهو الأعمال | 966675
Table No. (5) Workshop equipment
Supply, erection, testing and delivery in good working condition according to technical specifications and drawings for the following items
1 | Workshop equipment As shown in drawing and mechanical specification. | L.S | 1 | 175000 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
| المقاول contractor | الاستشارى consultant |  |  |  | PIU Manager رئيس وحدة تنفيذ المشروع | [5 empty] | اجمالي الصفحة | 28811533.544
| Signed التوقيع : | Signed التوقيع : |  |  | Signed التوقيع :
| Date التاريخ: | Date التاريخ: |  |  | Date التاريخ: |  |  |  |  | Chairman رئيس مجلس إدارة الشركة
Signed التوقيع :
Date التاريخ:
| ما قبله | [11 empty] | 28811533.544
Table No. (61 Miscellaneous equipment
Supply, erection, testing and delivery in good working condition according to technical specifications and drawings for the following items
1 | Dewatering pump set: Electrically operated As shown in drawing and mechanical specification. | NO. | 6 | 14800 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
2 | Travelling cranes. As shown in drawing and mechanical specification. | [6 empty] | 0
| For Raw Pumps (5 ton). | NO. | 1 | 99250 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
| for Treated Water Pumps (5 ton).. | NO. | 1 | 197000 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
| For Chlorine Cylinders (2 ton) | NO. | 1 | 65000 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
3 | Ventilating sets for RAW water and Treated water p.st As shown in drawing and mechanical specification. | L.S | 1 | 23600 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
4 | Traveling cran for generating station (10 ton) for W.T.P and (5) ton for intake. As shown in drawing and mechanical specification. | NO. | 1 | 215500 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
5 | Fir fighting system as shown in contracting drawing and firefighting specification . | L.S | 1 | 400000 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
| الاوناش الالماني |  |  | 200000 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
table No. (7) Spare parts
Supply, testing and delivery in good working condition according to technical specifications for the following items for raw water pump station
1 | Spare part for raw water pump | L.S | 1 | 93000 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
2 | Spare part for treated pump station | L.S | 1 | 180000 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
3 | Spare part for evacuating system | L.S | 1 | 75000 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
4 | Spare part for dewatering (for raw water pump room) | L.S | 1 | 8000 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
5 | Spare part for dewatering (for treated pump room) | L.S | 1 | 8000 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
6 | Spare part for chlorine building. | L.S | 1 | 72000 | 1 | 0 | 1 | 72000 |  | 0% | 100% |  | 72000
7 | Spare part for chemical house. | L.S | 1 | 132000 | 1 | 0 | 1 | 132000 |  | 0% | 100% |  | 132000
Supplying and erriction valves of W.T.P. units as shown in drawing and technical specifications as follow:
a- For Raw water pump station
| - For Gate valve (700 mm) | no | 3 | 41250 | [8 empty] | اسعار استرشادية
| For Gate valve (600 mm) | no | 3 | 27000
| For Non return Valve (600 mm) | no | 3 | 37500
e- For Alum building
| For Gate valve (75 mm) | no | 6 | 200
| For Gate valve (50 mm) | no | 3 | 150
| For Non return Valve (50 mm) | no | 3 | 150
Supplying and erriction pipes between W.T.P. units as shown in drawing and technical specifications as follow:
a- Pipes with diameter 1000 mm
| Main raw water deliver line | m | 114 | 8000
b- Pipes with diameter 900 mm
| Secondary raw water deliver line for one group of filters | m | 15 | 6250
c- Pipes with diameter 50 mm
| Chlorination injection line | m | 10 | 86
| Alum injection line | m | 10 | 86
| المقاول contractor | الاستشارى consultant |  |  |  | PIU Manager رئيس وحدة تنفيذ المشروع | [5 empty] | اجمالي الصفحة | 29015533.544
| Signed التوقيع : | Signed التوقيع : |  |  | Signed التوقيع :
| Date التاريخ: | Date التاريخ: |  |  | Date التاريخ: |  |  |  |  | Chairman رئيس مجلس إدارة الشركة
Signed التوقيع :
Date التاريخ:
| ما قبله | [11 empty] | 29015533.544
Electrical schedule of prices
Table No, (1) Power transformers
Supply, erection, testing and delivery in good working condition according to technical specifications and recommendation of electric company in area.
1- | Power transformers 11/0.4 KV- 2000 KVA - 4 wire - 50 HZ - complete with all accessories needed for good operation for the treatment plant and replaced instead the existing TRs. 1.5 MVA which in the pur water pump building. | L.S | 2 | 189000 | 2 | 0 | 2 | 378000 |  | 10% | 100% |  | 340200
2- | Power transformers Kiosk 11/0.4 KV- 1000 KVA - 4 wire - so HZ - complete with the transformers for the Intake. | L.S | 1 | 220564 | 1 | 0 | 1 | 220564 |  | 0% | 0% |  | 220564
* The above transformers is feeded through the same old outgoing feeders of the M.T switchgear.
Table No, (2) low- voltage switchqear & boards
| Supply, erection, testing and delivery in good working condition according to technical specifications and drawings for the following items | [6 empty] | 0
1 | Main Raw water pumping station L. voltage switch-board as drawings & specifications . | L.S | 1 | 1725000 | 1 | 0 | 1 | 1725000 |  | 0% | 100% | لحين التشغيل | 1725000
2 | Main treated water pumping station L. voltage Raw switch-board as drawings & specifications . | L.S | 1 | 3300000 | 0 | 1 | 1 | 3300000 |  | 10% | 100% | لحين التشغيل | 2970000
3 | Chemical house L.v Switch boards as drawings. | L.S | 1 | 7700 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
4 | Chlorination building L.v Switch boards as drawings. | L.S | 1 | 3000 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
5 | Spar parts for L.T switchgear for intake and treated water and chlorine and chemicals | L.S | 1 | 1500000 | 1 | 0 | 1 | 1500000 |  | 0% | 100% |  | 1500000
Table No. (3) cables
Supply, erection of P.V.C and armoured cables XLPE, P.V.C insulated and sheathed with copper conductors the price will include excavation and refilling, conduits, galvanized steel cable trays wherever required , laying and what's necessary
1 | Low- voltage cables 1/1.2KV for all boards , motors , instruments and what's mecessary as specifications and drawings for the Intake and treated water pump station and chlorine building and chemical house . | L.S | 1 | 2300000 | 1 | 0 | 1 | 2300000 |  | 92% | 100% | لحين توريد باقي الكابلات ونهو الأعمال | 184000
Table No, (4) Lighting
Supply, erection, testing and delivery in good working condition according to technical specifications and drawings for the following items
1 | Indoor lighting as drawings and specifications for In take | L.S | 1 | 15300 | 1 | 0 | 1 | 15300 |  | 40% | 100% | لحين نهو الأعمال | 9180
2 | Outdoor lighting as drawings and specifications for the intake | L.S | 1 | 125000 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
Table No. (5) Earthing system
Supply, erection, testing and delivery in good working condition according to technical specifications and drawings for the following items
1 | Earthing system for intake inclnding a- M.T switchgear b- transformers c- L.T switchgear d- equipments e- generator set f-motors and pumps note: earthing system must be carried out by a company specified in that type of works. | L.S | 1 | 35000 | 0 | 1 | 1 | 35000 |  | 0% | 100% |  | 35000
Table No. (6) standby diesel generating unit.
Supply, erection, testing and delivery in good working condition according to technical specifications and drawings for the following items
1 | Standby power plant includes: a-diesel generator set 1250KVA 3ph 380/220v, 50c/s for pure water plant. b- fiiel tanks, fuel transfer pumps, and all piping, valves, etc for fuel feeding, c- generator control cubicle, d- generator set spare parts as specified. | L.S | 1 | 1770000 | 1 | 0 | 1 | 1770000 |  | 15% | 100% | لحين نهو أعمال التركيب | 1504500
2 | The same above but 650 KVA 3 ph 380 /220 V - so - HZ for the intake . | L.S | 1 | 905000 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
3 | Any other equipment not mentioned and needed for the plant | L.S | 1
| المقاول contractor | الاستشارى consultant |  |  |  | PIU Manager رئيس وحدة تنفيذ المشروع | [5 empty] | اجمالي الاعمال | 37503977.544
| Signed التوقيع : | Signed التوقيع : |  |  | Signed التوقيع :
| Date التاريخ: | Date التاريخ: |  |  | Date التاريخ:
Chairman رئيس مجلس إدارة الشركة
Signed التوقيع :
Date التاريخ:
التشوينات
6.1 | pipes cast iron ductile diametar 1000 mm | m | 3930 | 2884 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
Mechanical Works
| Table No. (2)Raw water pumping station equipment | [11 empty] | 0
1 | Raw water pumping unit for new intake 600 Lit/sec at 30 ms head complete with driving motors. As shown in drawing and mechanical specification. | NO. | 3 | 223500 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
Table NO. (3) Treated water pumping station equipment.
1 | Treated water pumping unit 500 Lit/sec at 60 ms head complete with driving motors and all accessories As shown in drawing and mechanical specification. | NO. | 3 | 517500 | 3 | -3 | 0 | 0 |  |  | 0 |  | 0
Table No.(6) Miscellaneous equipment
1 | Dewatering pump set: Electrically operated As shown in drawing and mechanical specification. | NO. | 6 | 13837.5 | 4 | 0 | 4 | 55350 |  | 25% | 0 |  | 41512.5
4 | All pump suction pipes from Nil Revir up to pumps with diameter of 700 mm and all accessories. | m | 90.1 | 2615 | 0 | 0 | 0 | 0 |  | 0% | 0 |  | 0
electrical schedule of prices
table no (6) stand by diesel generating unit
1 | stand by power plant includes : adiesel generator set 1250 kva 3 ph 380 / 220 v, 50 c/s | L.s | 1 | 1687972.73 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0
2 | stand by power plant includes : adiesel generator set 650 kva 3 ph 380 / 220 v, 50 c/s | L.s | 1 | 905000 | 1 | 0 | 1 | 905000 |  | 28% | 0 |  | 651600
Table No, (1) Power transformers
1 | Power transformers 11/0.4 KV- 2000 KVA - 4 wire - 50 HZ - complete with all accessories needed for good operation for the treatment plant and replaced instead the existing TRs. 1.5 MVA which in the pur water pump building. | L.S | 2 | 189000 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0
2 | Power transformers Kiosk 11/0.4 KV- 1000 KVA - 4 wire - so HZ - complete with the transformers for the Intake. | L.S | 1 | 220564 | 0 | 0 | 0 | 0 |  |  |  |  | 0
1 | Table No, (2) low- voltage switchqear & boards
| Supply, erection, testing and delivery in good working condition according to technical specifications and drawings for the following items | [11 empty] | 0
1 | Main Raw water pumping station L. voltage switch-board as drawings & specifications . | L.S | 1 | 1061500 | 0 | 0 | 0 | 0 |  | 0% |  |  | 0
2 | Main treated water pumping station L. voltage Raw switch-board as drawings & specifications . | L.S | 1 | 2160000 | 1 | -1 | 0 | 0 |  | 0% |  |  | 0
3 | Chemical house L.v Switch boards as drawings. | L.S | 1 | 7600 | 1 | 0 | 1 | 7600 |  | 25% |  |  | 5700
4 | Chlorination building L.v Switch boards as drawings. | L.S | 1 | 2100 | 1 | 0 | 1 | 2100 |  | 25% |  |  | 1575
| Table No. (4) Chemical house equipment and Chlorination house equipment | [11 empty] | 0
1 | Alum injecting system equipment As shown in drawing and mechanical specification. | L.S | 1 | 666000 | 1 | 0 | 1 | 666000 |  | 25% |  |  | 499500
[11 empty] | اجمالي التشوينات |  | 1199887.5
[11 empty] | اجمالي الاعمال |  | 37503977.544
[11 empty] | Total الاجمالى |  | 38703865.044
[11 empty] | خصم 8.5% طبقا لعطاء المقاول |  | 3289828.5287
[11 empty] | الاجمالي بعد خصومات المقاول طبقا للتعاقد |  | 35414036.5153
[11 empty] | Total Revieved ما سبق صرفة |  | 33003808.71
[11 empty] | Invoice Total قيمة المستخلص الحالى |  | 2410227.8053
[11 empty] | %استهلاك الدفعة المقدمة 10 |  | 241022.7805
[11 empty] | Liability ضمان الاعمال |  | 481587.7185
[12 empty] | 10%غرامه التأخير | 241022.7805
[11 empty] | Net Invoice Total صافى المستخلص |  | 1446594.5257
| المقاول contractor | الاستشارى consultant |  |  |  | PIU Manager رئيس وحدة تنفيذ المشروع
| Signed التوقيع : | Signed التوقيع : |  |  | Signed التوقيع : |  |  |  |  | Chairman رئيس مجلس إدارة الشركة
| Date التاريخ: | Date التاريخ: |  |  | Date التاريخ: |  |  |  |  | Signed التوقيع :
Date التاريخ:
Note on B11: (600 L/s) for the first stage,
Note on E55: Usert1: بدلا من 1700ج

## Sheet1
1408
2860
0 | 3740
0 | 1600
0 | 3768
0 | 2475
20568
1235.1
37654.1